## BI
Customer Ref# | Finastra Ref# | Short Description | Feature | Given [Precondition] | When [Trigger] | Then [Result] | How [By setting] | Comment | Classification | Tracking Status | Due Date | Phase
Functional Rule n°016 Product Rule n°011 MCA. C/L 1 | BI_010 |  | BI invocation Point | Outgoing payment | Any outgoing non-future dated payment is received and invocation point is reached in the flow | Triggers a call to an external system for a balance check of a customer account to be debited |  | The exclusion of cross-ccy pre-booked deal payment is done in the interface selection rule - see below BI_070 This includes also cheque letter payments 16 Jan - after integration session | COTS Integration | Under discussion | 5.3.2018 | France
PAY.PR.05 | BI_030 |  | Bypass BI | Outgoing payment | Any future payment is received | On a processing date, triggers a call to an external system for a balance check of a customer account to be debited | Bypass Step rule Sub-type - BI to exclude future dated with processing date greater than today | The check shouldn't be performed on the received date, only on the processing date ZBA payment - to check Future requirement - internal departments payments | COTS Integration | Under discussion |  | France
| BI_070 |  | Interface Selection | Outgoing | BI invocation point is reached in the flow | The relevant BI interface is selected | Interface Selection rule to select the relevant interface with the exception of cross ccy pre-deal payments |  | COTS Integration | Under discussion | 5.3.2018 | France
| BI_080 |  | Interface Layout | Outgoing payment | BI invocation point is reached in the flow | The relevant BI interface is selected in Fndt message XML format | Interface Types - format definition | The layout will include the original payment in SWIFT format, with the full Fndt message extension with additional metadata with bulking details | COTS Integration | Under discussion | 5.3.2018 | France
| BI_090 |  | Interface Wait Behavior | Outgoing payment | Request is sent to BI interface | Payment is waiting for a response in order to proceed with the flow | Interface_Types - wait behavior attribute with default value to use the standard Balance Inquiry waiting queue |  | COTS Integration | Under discussion | 5.3.2018 | France
Functional Rule n°017 | BI_100 |  | Interface Inactive behavior | Outgoing payment | The following are the events that cause the interface to be Inactive: - After a configurable number of consecutive request transmission exceptions. - The interface is Inactive to begin with. - No response received from interface after a configurable time which results in Timeout. | The interface is Inactive Request is not created, stop the flow, and put the message in status the relevant stop status. When the interface is active again, create the request, send it and continue with the flow. | Interface_Types - stop after predefined number of connection exceptions, timeout definition and active/non active behavior |  | COTS Integration | Under discussion | 5.3.2018 | France