## FX
BRD Ref# | Finastra Ref# | Feature | Given [Precondition] | When [Trigger] | Then [Result] | How [By setting] | Comment | Classification | Tracking Status | Due Date | Phase
PFX.0.PR.001 PFX.0.PR.025 MCA. C/L 1 | FX_130 | FX invocation point | Outgoing/ Incoming BOOK payment | Any payment with a debit/credit side conversion is received (dr/cr account ccy <> pmt settlement ccy) and external FX point is reached in the flow | Triggers a call to an PFX interface on the processing date, which is calculated by ccy pair and MOP | Rate Usage pointing to the PFX interface | no conversion on onwards FX call for all cases includes cheque letter payments - 17 Jan cheque descoped. standard interface will be configured, next phase proprietary interface will be used. Pre-deals are not part of the France scope. Only EUR->other ccy, no USD->other ccy, etc. Technical clarifications will be closed after integration session | COTS Integration | Key in pending clarification | 5.3.2018 | France
PFX.0.PR.018 PFX.0.IN.003 PFX.0.IN.005 PFX.0.OM.001 PFX.ORE.001 Functional Rule n°018 | FX_170 | Response Handling | Outgoing/ Incoming BOOK payment | A successful response with a converted debit or credit amount is received and FX VD is the same as calculated VD | Apply received converted amount on the processed payment and audit the override action. Response data is saved in GPP repository for monitoring and reporting purposes |  | 1.by default FX interface returns a rate to calculate an amount applying of a converted amount is a change 2. after external call, GPP re-evaluates MOP & VD 17 jan - standard response for France phase, no VD adjustment, changing from Gap to COTS Integration Technical configuration after integration session | COTS Integration | Key in pending clarification | 5.3.2018 | France
PFX.1.PL.003 PFX.1.PR.012 PFX.0.IN.001 PFX.0.IN.002 PFX.0.IN.003 | FX_210 | Interface Layout | Outgoing/ Incoming BOOK payment | FX invocation point is reached in the flow and PFX interface is triggered including bulk reference | The relevant FX interface is selected in Fndt message XML format | Interface Types - format definition: Fndt message XML format with the original payment in SWIFT format and extension details with metadata | Major details: Request: FX deal ref (bulking by this ref), client id, dr/cr acc & ccy, calc VD, reverse sell ind, file ref, etc. Response: Fx deal ref validation ind, FX deal ref, VD, converted dr/cr amount&ccy, client rate & margin 17 jan - standard layout for France phase | COTS Integration | Key in pending clarification | 5.3.2018 | France
PFX.0.IN.001-005 | FX_220 | Interface Selection | Outgoing/ Incoming BOOK payment | FX invocation point is reached in the flow | The relevant FX interface is selected | Interface Selection rule to select the appropriate interface |  | COTS Integration | Key in pending clarification | 5.3.2018 | France
| FX_230 | Interface Wait Behavior | Outgoing/ Incoming BOOK payment | Request is sent to external FX | Payment waits untill response is received before continuing the process | Interface Types - wait behavior attribute with default value to use the standard FX wait queue | GPP will wait for PFX response apply manual rate is not required | COTS Integration | Key in pending clarification | 5.3.2018 | France
PFX.0.IN.004 PFX.0.PR.017 | FX_240 | Interface inactive behavior | Outgoing/ Incoming BOOK payment | 1.after a confugurable number of transmission exceptions 2.inactive interface 3.no response is received | The request is not created for inactive interface status, message stops in the dedicated stop queue until the interface is up and running | Interface Types - stop after predefined number of connection exceptions, timeout definition and active/non active behavior |  | COTS Integration | Key in pending clarification | 5.3.2018 | France